## Agile Project Backlog
Agile Product Backlog
SUMMARY
Project Description
Company Lockers Pvt Ltd aim to digitize their products and chose LockedMe.com. The goal of the company is to deliver a high end quality product as early as possible.
PROJECT BACKLOG
ID | As a | I want to | So that | Priority | Story point | Sprint Assignment | Status
[8 empty] | Comments relating to a story point changing, a new story added, or a story removed. | Initial numeric estimate (size) concluded during Sprint Review, Hours | Hours | Hours | Hours | Hours | Hours
1 | User | Retrive the file names | I can see how many and which files exists in the directory | Must | 4 |  | Done
2 | User | Perform file handling operations | I can create, delete and search for any file | Must | 8 |  | Done
3 | User | Close the application |  | Must | 2 |  | Done

## Agile Sprint Backlog
Agile Sprint Backlog
SUMMARY
CHANGE IN SCOPE
Original Story Points |  | 14
New Points |  | 0
Total Points |  | 14
CHANGE IN SCOPE |  | 0%
SPRINT BACKLOG
ID | Backlog task | Assigned to | Story points | New points? | Release | Status | Business value | Change management notes | Initial estimate
[8 empty] | Comments relating to a story point changing, a new story added, or a story removed. | Initial numeric estimate (size) concluded during Sprint Review, Hours
1 | As a User, I want to retrive the file names, so that I can view how many and which files are present in the directory.
1.1 | Code the… | Riyaz J |  | FALSE | 1 | Done | High
1.2 | Design the UI | Riyaz J |  | FALSE | 1 | Done | Low
1.3 | Unit test.. | Riyaz J |  | FALSE | 1 | Done | High
2 | As a User, I want to perform file handling operation, so that I can create, delete and search for any file.
2.1 | Code the file creation operation. | Riyaz J |  | FALSE | 1 | Done | High
2.2 | Code the file deletion operation. | Riyaz J |  | FALSE | 1 | Done | High
2.3 | Code the file search operation | Riyaz J |  | FALSE | 1 | Done | High
2.4 | Design the UI | Riyaz J |  | FALSE | 1 | Done | High
2.5 | Unit test | Riyaz J |  | FALSE | 1 | Done | High
3 | As a User, I want to close the program
3.1 | Code the.. | Riyaz J |  | FALSE | 1 | Done | High
3.1 | Design the UI | Riyaz J |  | FALSE | 1 | Done | High